## Sheet1
Weeks
| 2016-05-16 | 2016-05-23 | 2016-05-30 | 2016-06-06 | 2016-06-13 | 2016-06-20 | 2016-06-27 | 2016-07-04 | 2016-07-11 | 2016-07-18 | 2016-07-25 | 2016-08-01 | 2016-08-08 | 2016-08-15 | 2016-08-22 | 2016-08-29
Research: CNNs | 2016-08-22: CONTINGENCY
Research: Deep RL | bar: 2016-05-23 to 2016-06-06
Research: Deep Learning code solutions | bar: 2016-05-30 to 2016-06-06
Research: NEAT | bar: 2016-05-30 to 2016-06-13
Stub implementation of ViZDoom controller | bar: 2016-05-30
Create testing benchmark framework | bar: 2016-06-13
Create general evolutionary framework | bar: 2016-06-06
Implement basic RL policy | bar: 2016-06-20 to 2016-06-27
Implement evolutionary policy | bar: 2016-06-27 to 2016-07-04
Assemble final policy | bar: 2016-07-04 to 2016-07-18
Comparative test of all policies | bar: 2016-07-04 to 2016-08-01
Write Report: introduction | bar: 2016-06-13 to 2016-06-20
Write Report: background literature | bar: 2016-07-11 to 2016-07-18
Write Report: Methodology | bar: 2016-07-25 to 2016-08-01
Write Report: Experimental design and results | bar: 2016-08-01 to 2016-08-08
Write Report: Discussion and conclusions | bar: 2016-08-08 to 2016-08-15